## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Common | Admin, Manager | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | Done | iter1 | none
2 | Demo Dashboard | Common | Admin, Manager | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | Done | iter1 | none
3 | User Login | Common | Admin, Manager | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | iter1 | none
4 | Password Reset | Common | Admin, Manager | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | iter1 | none
5 | User Register | Common | Admin, Manager | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | iter1 | none
6 | User Profile | Common | Admin, Manager | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | iter1 | none
7 | Password Change | Common | Admin, Manager | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | iter1 | none
8 | Setting List | Admin | Admin, Manager | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | iter1 | none
9 | Setting Details | Admin | Admin, Manager | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | iter1 | none
10 | User List | Admin | Admin, Manager | - This screen display all information of all users in the system and managed by admin - Fuction: + Global: Sort (Columns), Paginate, Search + Row: View/Edit, Activate/Deactivate | DatLT | Done | iter1 | none
11 | User Details | Admin | Admin, Manager | - Show information of an user (Id, Full Name, Email, Mobile, Role, Status, Note,....) | DatLT | Done | iter1 | none
12 | Subject List | Manager | Admin, Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Done | iter1 | none
13 | Subject Details | Manager | Admin, Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | iter1 | none
14 | Web Contact List | Supporter | Admin, Manager | Show the list of assigned web contacts (By Email, Phone, Address,......) | DatLT | Done | iter1 | none
15 | Web Contact Details | Supporter | Admin, Manager | View/Edit an assigned web contact | DaiNH | Done | iter1 | none
16 | System Permissions | Admin | class, package, user, user_role, setting | Configure the page-access permissions for each of the system roles | KyNVC | Done | iter2 | none
17 | User Authorization | System | class, package, user, user_role, setting | Link Check, Sider Menu, Header & Footer | KyNVC | Done | iter2 | none
18 | Subject Setting List | Manager | class_setting | Cấu hình thông tin subject: complexity levels, quality levels | DaiNH | Done | iter2 | none
19 | Subject Setting Details | Manager | class_setting |  | DaiNH | Done | iter2 | none
20 | Assignment List | Manager | class_setting | Danh sách các assignment của môn học; lọc theo subject (1), status; search theo title | DaiNH | Done | iter2 | none
21 | Assignment Details | Manager | team |  | DatLT | Done | iter2 | none
22 | Eval Criteria List | Manager | team | Danh sách các tiêu chí đánh giá assignment; lọc theo subject (1), assignment (1), status; search theo criteria_name | DatLT | Done | iter2 | none
23 | Eval Criteria Details | Manager | user, class_user, team |  | DatLT | Done | iter2 | none
24 | Class List | Manager | user, class_user, team | Filters: Trainer, Term, Status Columns: Id, Package, Code, Term, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Package), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | AnhPT | Done | iter2 | none
25 | Class Details | Manager | user, class_user, team | Package (L), Code, Term (), Trainer (L), Status | AnhPT | Done | iter2 | none
26 | Class Setting List | Trainer | subject, lesson | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | KyNVC | Done | iter2 | none
27 | Class Setting Details | Trainer | subject, lesson | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | iter2 | none
28 | Milestone List | Trainer | class, subject, lesson, class_lesson | Danh sách các mốc thực hiện và nội dung các assignment của lớp học | HoangL | Done | iter2 | none
29 | New Milestone | Trainer | class, subject, lesson, class_lesson | Tạo mới một milestone, chọn based assignment từ danh sách các assignment của subject liên quan + nhập start date, end date Sau khi tạo thì thông tin assignment được chọn của subject cùng các tiêu chí đánh giá liên quan được copy vào thông tin milestone | HoangL | Done | iter2 | none
30 | Milestone Details | Trainer | user, setting, user_role, permission | Xem, sửa thông tin milestone của lớp học | HoangL | Done | iter2 | none
31 | Class Eval-Criteria List | Trainer | eval_criteria | List out the Evaluation Criteria for a specific class milestone in the system. The Supporter can view the Evaluation Criteria for the classes that he/she are assigned (read only) From this page, the user can link to the Class Eval-Criteria Details page for adding new (by cloning an existing Class Evaluation Criteria or adding brand new one) or updating a specific Class Evaluation Criteria | DatLT | Doing | iter3 | none
32 | Class Eval-Criteria Details | Trainer | eval_criteria | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | DaiNH | Doing | iter3 | none
33 | Trainee List | Supporter | class_user | List out the Trainees for a specific class in the system - The list also include the evaluated grades of the trainees (calculated automatically) - When changing trainee status to Dropped Out, the user need to input the dropout date - The Trainer also have the same access rights as the Supporter to the trainees list of the classes that he/she are assigned - From this page, the user can link to the Trainee Import & Trainee Details page s | KyNVC | Doing | iter3 | none
34 | Trainee Import | Supporter | user, class_user | This is a pop-up screen where the user can import the new trainee list into a specific class - The import file should include limitted trainee information (full name, email) - New class trainees would be added into the selected class. In case any user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) | KyNVC | Doing | iter3 | none
35 | Trainee Details | Supporter |  | Allow the user to input class trainee information for updating - The Trainer can also update class trainee information - Trainee basic information are read-only: full name, user name, email - Class trainee evaluation are read-only: on-going evaluation, final evaluation, topic evaluation - Class trainee information are editable: status, drop-out date, note | Not yet | Doing | iter3 | none
36 | Schedule List | Supporter | schedule, class, class_setting | List out class schedules - Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Action - Actions: + View/Edit: link to the Schedule Details page to view/edit the relevant class schedule + Take Attendance: link to Attendance Details page to add/edit the class attendance of the relevant slot - this link is available only durent the training day of that slot - Global actions: + View Attendance: link to Attendance Tracking page + Add New: link to the Schedule Details page to add new class schedule - The Trainer have similar permissions as the Supporter on this page | DaiNH | Doing | iter3 | none
37 | Schedule Details | Supporter | schedule, class, class_setting | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | DaiNH | Doing | iter3 | none
38 | Attendance Tracking | Trainer | attendance, schedule | Allow the Supporter/Trainer to view the class trainees' attendance status of all the class schedules | AnhPT | Doing | iter3 | none
39 | Attendance Details | Trainer | attendance, schedule | Allow the Supporter/Trainer to add/edit the class attendance of the relevant schedule | AnhPT | Doing | iter3 | none
40 | Schedule Attendace | Trainee | attendance, schedule | List out class schedules of the selected class & the student attendance status for each schedule Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Attendance Status | HoangL | Doing | iter3 | none
41 | Team List | Trainer | team, team_member | See the Mockup - The Supporter & Trainee can view the team list & team details - Member Actions: Change Team, Remove Member, Set As Team Leader - Global Actions: Group or Regroup - link to New Teams page to create/re-create new team set - Team Actions: + Add New Trainee: add trainee(s) from weighting list into the selected team + Add New: link to Team Details to add new team to the milestone team set + Team Details: link to Team Details to view and/or edit the team + Activate/Deactivate: activate or deactiavate the team - The above actions are not allowed for the team sets which are "attached" to the in-progress or closed milestones | DatLT | Doing | iter3 | none
42 | New Teams | Trainer | team, team_member, submit | Allow the user to create groups or regroups See the Mockup - note to add one more tab called Clone Group with the similar layout as the Reuse Group; Clone Groups would create new team set "attached" to the milestone (by copying the current team configurations) instead of re-using the current team set in the Reuse Groups | KyNVC | Doing | iter3 | none
43 | Team Details | Trainer | team, team_member, submit | Allow the user to input team information for updating relevant team or adding new team to the team set of the milestone. - Fields: team code, topic name, status, description - When creating new team, the default status value is Active | AnhPT | Doing | iter3 | none
44 | Issue List | Trainee | issue | DS các issues, lọc theo [Class, Milestone, Author, Assignee, Issue Type(s), Issue Status] + tìm kiếm theo issue title + chọn sắp xếp tăng/giảm dần theo cột cụ thể => tham khảo cơ chế lọc/search/sort của GitLab Trainee có thể click nút Đồng bộ GitLab để lấy thông tin issues mới nhất từ GitLab về | HoangL | Doing | iter3 | none
45 | Issue Details | Trainee | issue | View thông tin issue chi tiết + lịch sử thay đổi issue; với các issue mà trainee đang đóng vai trò author hoặc assignee thì trainee có thể link/update thông tin link issue vào các requirement issues cụ thể & sau khi update thì thông tin mapping sẽ được tự động đồng bộ lên GitLab (tham khảo cơ chế link issue trong GitLab) | HoangL | Doing | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | Done | Iter1 | Iter1
2 | Demo Dashobard | Common | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | To Do | Iter1 | Iter1
3 | User Login | Common | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | Iter1 | Iter1
4 | Password Reset | Common | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | Iter1 | Iter1
5 | User Register | Common | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | Iter1 | Iter1
6 | User Profile | Common | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | Iter1 | Iter1
7 | Password Change | Common | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | Iter1 | Iter1
8 | Setting List | Admin | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | Iter1 | Iter1
9 | Setting Details | Admin | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | Iter1 | Iter1
10 | User List | Admin | Filters: Role, Status Column: Id, Full Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Full Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | DatLT | Done | Iter1 | Iter1
11 | User Details | Admin | Fields: Id, Full Name, Email, Mobile, Role, Status, Note | DatLT | Done | Iter1 | Iter1
12 | Subject List | Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Done | Iter1 | Iter1
13 | Subject Details | Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | Iter1 | Iter1
14 | Web Contact List | Supporter | Show the list of assigned web contacts | DatLT | Done | Iter1 | Iter1
15 | Web Contact Details | Supporter | View/Edit an assigned web contact | DaiNH | Done | Iter1 | Iter1

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | System Permissions | Admin | Configure the page-access permissions for each of the system roles | KyNVC | Doing | Iter2 | Iter2
2 | User Authorization | System | Link Check, Sider Menu, Header & Footer | KyNVC | Doing | Iter2 | Iter2
3 | Subject Setting List | Manager | Cấu hình thông tin subject: complexity levels, quality levels | DaiNH | Done | Iter2 | Iter2
4 | Subject Setting Details | Manager |  | DaiNH | Done | Iter2 | Iter2
5 | Assignment List | Manager | Danh sách các assignment của môn học; lọc theo subject (1), status; search theo title | DaiNH | Done | Iter2 | Iter2
6 | Assignment Details | Manager |  | DatLT | Done | Iter2 | Iter2
7 | Eval Criteria List | Manager | Danh sách các tiêu chí đánh giá assignment; lọc theo subject (1), assignment (1), status; search theo criteria_name | DatLT | Done | Iter2 | Iter2
8 | Eval Criteria Details | Manager |  | DatLT | Done | Iter2 | Iter2
9 | Class List | Manager | Filters: Trainer, Term, Status Columns: Id, Package, Code, Term, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Package), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | AnhPT | Done | Iter2 | Iter2
10 | Class Details | Manager | Package (L), Code, Term (), Trainer (L), Status | AnhPT | Done | Iter2 | Iter2
11 | Class Setting List | Trainer | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | KyNVC | Done | Iter2 | Iter2
12 | Class Setting Details | Trainer | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | Iter2 | Iter2
13 | Milestone List | Trainer | Danh sách các mốc thực hiện và nội dung các assignment của lớp học | HoangL | Done | Iter2 | Iter2
14 | New Milestone | Trainer | Tạo mới một milestone, chọn based assignment từ danh sách các assignment của subject liên quan + nhập start date, end date Sau khi tạo thì thông tin assignment được chọn của subject cùng các tiêu chí đánh giá liên quan được copy vào thông tin milestone | HoangL | Done | Iter2 | Iter2
15 | Milestone Details | Trainer | Xem, sửa thông tin milestone của lớp học | HoangL | Done | Iter2 | Iter2

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Class Eval-Criteria List | Trainer | List out the Evaluation Criteria for a specific class milestone in the system. The Supporter can view the Evaluation Criteria for the classes that he/she are assigned (read only) From this page, the user can link to the Class Eval-Criteria Details page for adding new (by cloning an existing Class Evaluation Criteria or adding brand new one) or updating a specific Class Evaluation Criteria | DatLT | To Do | Iter3 | Iter3
2 | Class Eval-Criteria Details | Trainer | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | DaiNH | To Do | Iter3 | Iter3
3 | Trainee List | Supporter | List out the Trainees for a specific class in the system - The list also include the evaluated grades of the trainees (calculated automatically) - When changing trainee status to Dropped Out, the user need to input the dropout date - The Trainer also have the same access rights as the Supporter to the trainees list of the classes that he/she are assigned - From this page, the user can link to the Trainee Import & Trainee Details page s | KyNVC | To Do | Iter3 | Iter3
4 | Trainee Import | Supporter | This is a pop-up screen where the user can import the new trainee list into a specific class - The import file should include limitted trainee information (full name, email) - New class trainees would be added into the selected class. In case any user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) | KyNVC | To Do | Iter3 | Iter3
5 | Trainee Details | Supporter | Allow the user to input class trainee information for updating - The Trainer can also update class trainee information - Trainee basic information are read-only: full name, user name, email - Class trainee evaluation are read-only: on-going evaluation, final evaluation, topic evaluation - Class trainee information are editable: status, drop-out date, note | Not yet | To Do | Iter3 | Iter3
6 | Schedule List | Supporter | List out class schedules - Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Action - Actions: + View/Edit: link to the Schedule Details page to view/edit the relevant class schedule + Take Attendance: link to Attendance Details page to add/edit the class attendance of the relevant slot - this link is available only durent the training day of that slot - Global actions: + View Attendance: link to Attendance Tracking page + Add New: link to the Schedule Details page to add new class schedule - The Trainer have similar permissions as the Supporter on this page | DaiNH | To Do | Iter3 | Iter3
7 | Schedule Details | Supporter | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | DaiNH | To Do | Iter3 | Iter3
8 | Attendance Tracking | Trainer | Allow the Supporter/Trainer to view the class trainees' attendance status of all the class schedules | AnhPT | To Do | Iter3 | Iter3
9 | Attendance Details | Trainer | Allow the Supporter/Trainer to add/edit the class attendance of the relevant schedule | AnhPT | To Do | Iter3 | Iter3
10 | Schedule Attendace | Trainee | List out class schedules of the selected class & the student attendance status for each schedule Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Attendance Status | HoangL | To Do | Iter3 | Iter3
11 | Team List | Trainer | See the Mockup - The Supporter & Trainee can view the team list & team details - Member Actions: Change Team, Remove Member, Set As Team Leader - Global Actions: Group or Regroup - link to New Teams page to create/re-create new team set - Team Actions: + Add New Trainee: add trainee(s) from weighting list into the selected team + Add New: link to Team Details to add new team to the milestone team set + Team Details: link to Team Details to view and/or edit the team + Activate/Deactivate: activate or deactiavate the team - The above actions are not allowed for the team sets which are "attached" to the in-progress or closed milestones | DatLT | To Do | Iter3 | Iter3
12 | New Teams | Trainer | Allow the user to create groups or regroups See the Mockup - note to add one more tab called Clone Group with the similar layout as the Reuse Group; Clone Groups would create new team set "attached" to the milestone (by copying the current team configurations) instead of re-using the current team set in the Reuse Groups | KyNVC | To Do | Iter3 | Iter3
13 | Team Details | Trainer | Allow the user to input team information for updating relevant team or adding new team to the team set of the milestone. - Fields: team code, topic name, status, description - When creating new team, the default status value is Active | AnhPT | To Do | Iter3 | Iter3
14 | Issue List | Trainee | DS các issues, lọc theo [Class, Milestone, Author, Assignee, Issue Type(s), Issue Status] + tìm kiếm theo issue title + chọn sắp xếp tăng/giảm dần theo cột cụ thể => tham khảo cơ chế lọc/search/sort của GitLab Trainee có thể click nút Đồng bộ GitLab để lấy thông tin issues mới nhất từ GitLab về | HoangL | To Do | Iter3 | Iter3
15 | Issue Details | Trainee | View thông tin issue chi tiết + lịch sử thay đổi issue; với các issue mà trainee đang đóng vai trò author hoặc assignee thì trainee có thể link/update thông tin link issue vào các requirement issues cụ thể & sau khi update thì thông tin mapping sẽ được tự động đồng bộ lên GitLab (tham khảo cơ chế link issue trong GitLab) | HoangL | To Do | Iter3 | Iter3

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4