## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Common | Admin, Manager | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | To Do | iter1 | none
2 | Demo Dashboard | Common | Admin, Manager | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | To Do | iter1 | none
3 | User Login | Common | Admin, Manager | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | iter1 | none
4 | Password Reset | Common | Admin, Manager | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | iter1 | none
5 | User Register | Common | Admin, Manager | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | iter1 | none
6 | User Profile | Common | Admin, Manager | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | iter1 | none
7 | Password Change | Common | Admin, Manager | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | iter1 | none
8 | Setting List | Admin | Admin, Manager | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | iter1 | none
9 | Setting Details | Admin | Admin, Manager | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | iter1 | none
10 | User List | Admin | Admin, Manager | - This screen display all information of all users in the system and managed by admin - Fuction: + Global: Sort (Columns), Paginate, Search + Row: View/Edit, Activate/Deactivate | DatLT | Done | iter1 | none
11 | User Details | Admin | Admin, Manager | - Show information of an user (Id, Full Name, Email, Mobile, Role, Status, Note,....) | DatLT | Done | iter1 | none
12 | Subject List | Manager | Admin, Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Doing | iter1 | none
13 | Subject Details | Manager | Admin, Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | iter1 | none
14 | Web Contact List | Supporter | Admin, Manager | Show the list of assigned web contacts (By Email, Phone, Address,......) | DatLT | Done | iter1 | none
15 | Web Contact Details | Supporter | Admin, Manager | View/Edit an assigned web contact | DaiNH | Done | iter1 | none
16 | Class List | Manager | class, package, user, user_role, setting | Filters: Trainer, Term, Status Columns: Id, Package, Code, Term, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Package), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | Not yet | Doing | iter2 | none
17 | Class Details | Manager | class, package, user, user_role, setting | Package (L), Code, Term (), Trainer (L), Status | Not yet | Doing | iter2 | none
18 | Class Setting List | Trainer | class_setting | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | Not yet | Doing | iter2 | none
19 | Class Setting Details | Trainer | class_setting | Fields: Type (L), Title, Value, Display Order, Status, Description | Not yet | Doing | iter2 | none
20 | Class Setting Sync | System | class_setting | Whenever there is a change to the issue types, issue statuses, or function statuses, the new/updated information would be sent and synchronized automatically in the GitLab group (relevant to the selected class) in the form of the labels | Not yet | Doing | iter2 | none
21 | Team List | Trainer | team | Columns: Id, Team Code, Topic Code, Topic Name, Status The list is sort automatically by the Team Code Row Actions: View/Edit, Activate/Deactivate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | Not yet | Doing | iter2 | none
22 | Team Details | Trainer | team | Team Code, Topic Code, Topic Name, Status, Description | Not yet | Doing | iter2 | none
23 | Student List | Trainer | user, class_user, team | Filters: Team, Status Columns: Team, Full Name, Email, Team Leader, Status The list is sort automatically by the Team Code Row Actions: Change Team, Set As Team Leader, Activate/Deactivate Global Actions: Filter, Search (by Full Name, Email), Export Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | Not yet | Doing | iter2 | none
24 | Student Import | Trainer | user, class_user, team | Team, Full Name, Email, Team Leader, Status | Not yet | Doing | iter2 | none
25 | Student Sync | System | user, class_user, team | This job is called automatically after importing students. The job's purpose is to synchronize the user information to GitLab so that students can get access to the GitLab project then | Not yet | Doing | iter2 | none
26 | Lesson List | Expert | subject, lesson | List of lessons for a specific subject group by content module | Not yet | Doing | iter2 | none
27 | Lesson Details | Expert | subject, lesson | View/Add/Edit a subject lesson | Not yet | Doing | iter2 | none
28 | Class Lesson List | Trainer | class, subject, lesson, class_lesson | List the lessons for selected class grouped by training slots | Not yet | Doing | iter2 | none
29 | Class Lesson Details | Trainer | class, subject, lesson, class_lesson | View/Add/Edit or selected a subject lesson to use as class lesson | Not yet | Doing | iter2 | none
30 | System Permissions | Admin | user, setting, user_role, permission | Configure the page-access permissions for each of the system roles | Not yet | Doing | iter2 | none
31 | User Authorization | System | user, setting, user_role, permission | Link Check, Sider Menu, Header & Footer | Not yet | Doing | iter2 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | Done | Iter1 | Iter1
2 | Demo Dashobard | Common | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | To Do | Iter1 | Iter1
3 | User Login | Common | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | Iter1 | Iter1
4 | Password Reset | Common | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | Iter1 | Iter1
5 | User Register | Common | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | Iter1 | Iter1
6 | User Profile | Common | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | Iter1 | Iter1
7 | Password Change | Common | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | Iter1 | Iter1
8 | Setting List | Admin | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | Iter1 | Iter1
9 | Setting Details | Admin | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | Iter1 | Iter1
10 | User List | Admin | Filters: Role, Status Column: Id, Full Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Full Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | DatLT | Done | Iter1 | Iter1
11 | User Details | Admin | Fields: Id, Full Name, Email, Mobile, Role, Status, Note | DatLT | Done | Iter1 | Iter1
12 | Subject List | Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Done | Iter1 | Iter1
13 | Subject Details | Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | Iter1 | Iter1
14 | Web Contact List | Supporter | Show the list of assigned web contacts | DatLT | Done | Iter1 | Iter1
15 | Web Contact Details | Supporter | View/Edit an assigned web contact | DaiNH | Done | Iter1 | Iter1

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | System Permissions | Admin | Configure the page-access permissions for each of the system roles | KyNVC | Doing | Iter2 | Iter2
2 | User Authorization | System | Link Check, Sider Menu, Header & Footer | KyNVC | Doing | Iter2 | Iter2
3 | Subject Setting List | Manager | Cấu hình thông tin subject: complexity levels, quality levels | DaiNH | Done | Iter2 | Iter2
4 | Subject Setting Details | Manager |  | DaiNH | Done | Iter2 | Iter2
5 | Assignment List | Manager | Danh sách các assignment của môn học; lọc theo subject (1), status; search theo title | DaiNH | Done | Iter2 | Iter2
6 | Assignment Details | Manager |  | DatLT | Done | Iter2 | Iter2
7 | Eval Criteria List | Manager | Danh sách các tiêu chí đánh giá assignment; lọc theo subject (1), assignment (1), status; search theo criteria_name | DatLT | Done | Iter2 | Iter2
8 | Eval Criteria Details | Manager |  | DatLT | Done | Iter2 | Iter2
9 | Class List | Manager | Filters: Trainer, Term, Status Columns: Id, Package, Code, Term, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Package), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | AnhPT | Doing | Iter2 | Iter2
10 | Class Details | Manager | Package (L), Code, Term (), Trainer (L), Status | AnhPT | Doing | Iter2 | Iter2
11 | Class Setting List | Trainer | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | KyNVC | Doing | Iter2 | Iter2
12 | Class Setting Details | Trainer | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Doing | Iter2 | Iter2
13 | Milestone List | Trainer | Danh sách các mốc thực hiện và nội dung các assignment của lớp học | HoangL | Doing | Iter2 | Iter2
14 | New Milestone | Trainer | Tạo mới một milestone, chọn based assignment từ danh sách các assignment của subject liên quan + nhập start date, end date Sau khi tạo thì thông tin assignment được chọn của subject cùng các tiêu chí đánh giá liên quan được copy vào thông tin milestone | HoangL | Doing | Iter2 | Iter2
15 | Milestone Details | Trainer | Xem, sửa thông tin milestone của lớp học | HoangL | Doing | Iter2 | Iter2

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Class Eval-Criteria List | Trainer | Danh sách các tiêu chí đánh giá assignment của lớp; lọc theo class (1), milestone (1), status; search theo criteria_name | DatLT | To Do | Iter3 | Iter3
2 | Class Eval-Criteria Details | Trainer |  | HoangL | To Do | Iter3 | Iter3
3 | Trainee List | Supporter | Filters: Class, Status Columns: Class, Full Name, User Name, Email, Status, Dropout Date Row Actions: Activate/Dropout/Deactivate Global Actions: Filter, Search (by Full Name, User Name, Email), Export Roles: supporter~import/export, trainer ~ update status (with date & note in a PopUp) Status: Active, Dropout, Inactive | KyNVC | To Do | Iter3 | Iter3
4 | Trainee Import | Supporter | PopUp: template download link, class-choosing combo-box, file browser Excel: Full Name, User Name, Email, Status, Dropout Date | KyNVC | To Do | Iter3 | Iter3
5 | Team List | Trainer | Columns: Id, Team Code, Topic Name, Status, MilestoneXX The list is sort automatically by the Team Code Row Actions: View/Edit, Activate/Deactivate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | DatLT | To Do | Iter3 | Iter3
6 | Team Details | Trainer | Tab1-Team Overview: - Team Code, Status, Topic Name - Assigments (name, from, to), - Description Tab2-Team Members: Search, Add, Remove, Assign as TeamLead | DatLT | To Do | Iter3 | Iter3
7 | Tracking List | Trainee | Ref: SPM-Tracking List | DaiNH | To Do | Iter3 | Iter3
8 | New Tracking | Trainee | Ref: SPM-New Tracking | DaiNH | To Do | Iter3 | Iter3
9 | Tracking Details | Trainee | Ref: SPM-Tracking Details | DaiNH | To Do | Iter3 | Iter3
10 | Assignment Submits | Trainee | Ref: SPM-Milestone Submit & Tracking Submit; Trainee submit bài cá nhân, Team Leader submit bài theo nhóm | KyNVC | To Do | Iter3 | Iter3
11 | Class Evaluations | Evaluation |  | HoangL | To Do | Iter3 | Iter3
12 | Milestone Evaluations | Evaluation | Ref: SPM-Iteration Evaluations & SPM-Evaluation Import | HoangL | To Do | Iter3 | Iter3
13 | Trainee Evaluations | Evaluation | Ref: SPM-Student Evaluations | AnhPT | To Do | Iter3 | Iter3
14 | LOC Evaluation | Evaluation | Ref: SPM-LOC Evaluation | AnhPT | To Do | Iter3 | Iter3
15 | Tracking Updates | Trainee | Tracking Updates | AnhPT | To Do | Iter3 | Iter3

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4