## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Prepare context diagram in the SRS |  | 1 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/1 | Closed | Kien Fu | 2022-09-08 05:17 | 2022-09-13 05:17 | iter0 | 3_Done
add document | 1. Add Project Tracking 2. Add SDS Document 3. Add SRS Document | 2 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/2 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-13 06:54 | 2022-09-18 06:54 | iter1 | 3_Done
Setup environment | - Setup Maven and dependency | 3 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/3 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-13 07:11 | 2022-09-18 07:11 | iter1 | 3_Done
Design package | - Design project folder and package | 4 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/4 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-13 07:13 | 2022-09-18 07:13 | iter1 | 3_Done
Account login and permission | - Code login system and permission manager | 5 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/5 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-13 07:16 | 2022-09-18 07:16 | iter1 | 3_Done | User Login
Account register | Add register account function. | 6 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/6 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:18 | 2022-09-18 07:18 | iter1 | 1_To Do | User Register
Account password reset | - add password reset function | 7 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/7 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:19 | 2022-09-18 07:19 | iter1 | 1_To Do | Password Reset
Design home page | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | 8 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/8 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:23 | 2022-09-18 07:23 | iter1 | 1_To Do | Home Page
Design dashboard | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | 9 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/9 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:24 | 2022-09-18 07:24 | iter1 | 1_To Do | Demo Dashobard
User profile | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | 10 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/10 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:26 | 2022-09-18 07:26 | iter1 | 1_To Do | User profile
Password Change | Fields: Current Password, New Password, Verifying Password | 11 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/11 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:26 | 2022-09-18 07:26 | iter1 | 1_To Do | Password Change
Setting List | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | 12 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/12 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:27 | 2022-09-18 07:27 | iter1 | 1_To Do | Setting List
Setting Details | Fields: Type (L), Title, Value, Display Order, Status, Description | 13 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/13 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:28 | 2022-09-18 07:28 | iter1 | 1_To Do
User List | - This screen display all information of all users in the system and managed by admin - Fuction: + Global: Sort (Columns), Paginate, Search + Row: View/Edit, Activate/Deactivate | 14 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/14 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:29 | 2022-09-18 07:29 | iter1 | 2_Doing | Setting Details
User Details | - Show information of an user (Id, Full Name, Email, Mobile, Role, Status, Note,....) | 15 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/15 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:30 | 2022-09-18 07:30 | iter1 | 2_Doing | User Details
Subject List | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | 16 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/16 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:30 | 2022-09-18 07:30 | iter1 | 1_To Do | Subject List
Subject Details | Fields: Code, Name, Manager (L), Expert (L), Status, Description | 17 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/17 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:32 | 2022-09-18 07:32 | iter1 | 1_To Do | Subject Details
Web Contact List | Show the list of assigned web contacts (By Email, Phone, Address,......) | 18 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/18 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:32 | 2022-09-18 07:32 | iter1 | 2_Doing | Web Contact List
Web Contact Details | View/Edit an assigned web contact | 19 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/19 | Open | Nguyễn Văn Cao Kỳ | 2022-09-13 07:33 | 2022-09-18 07:33 | iter1 | 1_To Do | Web Contact Details
User Login Screen | Design Login Screen | 20 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/21 | Open | Nguyễn Văn Cao Kỳ | 2022-09-17 17:47 | 2022-09-22 17:47 | iter1 | 2_Doing,Task | User Login Screen
Write SRS for User Login screen |  | 21 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/22 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-17 17:50 | 2022-09-22 17:50 | iter1 | 3_Done,Task | User Login Screen
Write SDS for User Login screen |  | 22 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/23 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-17 17:51 | 2022-09-22 17:51 | iter1 | 3_Done,Task | User Login Screen
Write Code for User Login screen |  | 23 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/24 | Open | Nguyễn Văn Cao Kỳ | 2022-09-17 17:51 | 2022-09-22 17:51 | iter1 | 2_Doing,Task | User Login Screen
Integrate User Login screen with others |  | 24 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/25 | Open | Nguyễn Văn Cao Kỳ | 2022-09-17 17:52 | 2022-09-22 17:52 | iter1 | 2_Doing,Task | User Login Screen
Write Functional requirement for Password Change, Setting List, Setting Detail |  | 25 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/26 | Open | Pham Tuan Anh (K14 HL) | 2022-09-18 02:22 | 2022-09-23 02:22 | iter1 | 3_Done
Write SDS for Password Change, Setting List, Setting Detail |  | 26 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/27 | Open | Pham Tuan Anh (K14 HL) | 2022-09-18 02:25 | 2022-09-23 02:25 | iter1 | 1_To Do
Code Password Change screen |  | 27 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/28 | Open | Pham Tuan Anh (K14 HL) | 2022-09-18 02:28 | 2022-09-23 02:28 | iter1 | 1_To Do | Password Change
Code Setting List screen |  | 28 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/29 | Open | Pham Tuan Anh (K14 HL) | 2022-09-18 02:29 | 2022-09-23 02:29 | iter1 | 1_To Do | Setting List
Code Setting Detail screen |  | 29 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/30 | Open | Pham Tuan Anh (K14 HL) | 2022-09-18 02:30 | 2022-09-23 02:30 | iter1 | 1_To Do | Setting Detail
Security upgrade mysql:mysql-connector-java from 8.0.28 to 8.0.29 |  | 30 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/31 | Closed | Nguyễn Văn Cao Kỳ | 2022-09-18 08:13 | 2022-09-23 08:13 | iter1 | 3_Done
Write Functional requirement for User list, User detail, Web Contact list | Add all description to docs. | 31 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/32 | Open | Lai The Dat (K16_HL) | 2022-09-18 09:25 | 2022-09-23 09:25 | iter1 | 2_Doing
Create Mockup Screen for User list, User Detail, Web contact list | Design Mockup Screen | 32 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/33 | Open | Lai The Dat (K16_HL) | 2022-09-18 09:35 | 2022-09-23 09:35 | iter1 | 2_Doing
Write functional requirement for Home Page |  | 33 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/34 | Open | Le Hoang (K14_HL) | 2022-09-18 09:49 | 2022-09-23 09:49 | iter1 | 2_Doing,Task | Home Page
Write functional requirement for Demo Dashboard |  | 34 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/35 | Open | Le Hoang (K14_HL) | 2022-09-18 09:50 | 2022-09-23 09:50 | iter1 | 2_Doing,Task | Demo Dashboard
Write functional requirement for User Profile |  | 35 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/36 | Open | Le Hoang (K14_HL) | 2022-09-18 09:51 | 2022-09-23 09:51 | iter1 | 2_Doing,Task | User Profile
Create Mockup Screen for Home Page |  | 36 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/37 | Open | Le Hoang (K14_HL) | 2022-09-18 09:51 | 2022-09-23 09:51 | iter1 | 2_Doing,Task | Home Page
Create Mockup Screen for Demo Dashboard |  | 37 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/38 | Open | Le Hoang (K14_HL) | 2022-09-18 09:52 | 2022-09-23 09:52 | iter1 | 2_Doing,Task | Demo Dashboard
Create Mockup Screen for User Profile |  | 38 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/39 | Open | Le Hoang (K14_HL) | 2022-09-18 09:52 | 2022-09-23 09:52 | iter1 | 2_Doing,Task | User Profile
Code Home Page Screen |  | 39 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/40 | Open | Le Hoang (K14_HL) | 2022-09-18 09:53 | 2022-09-23 09:53 | iter1 | 2_Doing,Task | Home Page
Code Demo Dashboard Screen |  | 40 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/41 | Open | Le Hoang (K14_HL) | 2022-09-18 09:54 | 2022-09-23 09:54 | iter1 | 2_Doing,Task | Demo Dashboard
Code User Profile Screen |  | 41 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/42 | Open | Le Hoang (K14_HL) | 2022-09-18 09:54 | 2022-09-23 09:54 | iter1 | 2_Doing,Task | User Profile
Create mockup for subject list, subject details and web contact details |  | 42 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/43 | Open | Nguyen Huu Dai (K16_HL) | 2022-09-18 11:07 | 2022-09-23 11:07 | iter1 | 2_Doing
Write requirement function for subject list, subject details and web contact details |  | 43 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/44 | Open | Nguyen Huu Dai (K16_HL) | 2022-09-18 11:08 | 2022-09-23 11:08 | iter1 | 2_Doing