## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Common | Admin, Manager | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | Done | iter1 | none
2 | Demo Dashboard | Common | Admin, Manager | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | Done | iter1 | none
3 | User Login | Common | Admin, Manager | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | iter1 | none
4 | Password Reset | Common | Admin, Manager | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | iter1 | none
5 | User Register | Common | Admin, Manager | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | iter1 | none
6 | User Profile | Common | Admin, Manager | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | iter1 | none
7 | Password Change | Common | Admin, Manager | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | iter1 | none
8 | Setting List | Admin | Admin, Manager | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | iter1 | none
9 | Setting Details | Admin | Admin, Manager | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | iter1 | none
10 | User List | Admin | Admin, Manager | - This screen display all information of all users in the system and managed by admin - Fuction: + Global: Sort (Columns), Paginate, Search + Row: View/Edit, Activate/Deactivate | DatLT | Done | iter1 | none
11 | User Details | Admin | Admin, Manager | - Show information of an user (Id, Full Name, Email, Mobile, Role, Status, Note,....) | DatLT | Done | iter1 | none
12 | Subject List | Manager | Admin, Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Done | iter1 | none
13 | Subject Details | Manager | Admin, Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | iter1 | none
14 | Web Contact List | Supporter | Admin, Manager | Show the list of assigned web contacts (By Email, Phone, Address,......) | DatLT | Done | iter1 | none
15 | Web Contact Details | Supporter | Admin, Manager | View/Edit an assigned web contact | DaiNH | Done | iter1 | none
16 | System Permissions | Admin | class, package, user, user_role, setting | Configure the page-access permissions for each of the system roles | KyNVC | Done | iter2 | none
17 | User Authorization | System | class, package, user, user_role, setting | Link Check, Sider Menu, Header & Footer | KyNVC | Done | iter2 | none
18 | Subject Setting List | Manager | class_setting | Cấu hình thông tin subject: complexity levels, quality levels | DaiNH | Done | iter2 | none
19 | Subject Setting Details | Manager | class_setting |  | DaiNH | Done | iter2 | none
20 | Assignment List | Manager | class_setting | Danh sách các assignment của môn học; lọc theo subject (1), status; search theo title | DaiNH | Done | iter2 | none
21 | Assignment Details | Manager | team |  | DatLT | Done | iter2 | none
22 | Eval Criteria List | Manager | team | Danh sách các tiêu chí đánh giá assignment; lọc theo subject (1), assignment (1), status; search theo criteria_name | DatLT | Done | iter2 | none
23 | Eval Criteria Details | Manager | user, class_user, team |  | DatLT | Done | iter2 | none
24 | Class List | Manager | user, class_user, team | Filters: Trainer, Term, Status Columns: Id, Package, Code, Term, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Package), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | AnhPT | Done | iter2 | none
25 | Class Details | Manager | user, class_user, team | Package (L), Code, Term (), Trainer (L), Status | AnhPT | Done | iter2 | none
26 | Class Setting List | Trainer | subject, lesson | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | KyNVC | Done | iter2 | none
27 | Class Setting Details | Trainer | subject, lesson | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | iter2 | none
28 | Milestone List | Trainer | class, subject, lesson, class_lesson | Danh sách các mốc thực hiện và nội dung các assignment của lớp học | HoangL | Done | iter2 | none
29 | New Milestone | Trainer | class, subject, lesson, class_lesson | Tạo mới một milestone, chọn based assignment từ danh sách các assignment của subject liên quan + nhập start date, end date Sau khi tạo thì thông tin assignment được chọn của subject cùng các tiêu chí đánh giá liên quan được copy vào thông tin milestone | HoangL | Done | iter2 | none
30 | Milestone Details | Trainer | user, setting, user_role, permission | Xem, sửa thông tin milestone của lớp học | HoangL | Done | iter2 | none
31 | Class Eval-Criteria List | Trainer | eval_criteria | List out the Evaluation Criteria for a specific class milestone in the system. The Supporter can view the Evaluation Criteria for the classes that he/she are assigned From this page, the user can link to the Class Eval-Criteria Details page for adding new (by cloning an existing Class Evaluation Criteria or adding brand new one) or updating a specific Class Evaluation Criteria | HoangL | Done | iter3 | none
32 | Class Eval-Criteria Details | Trainer | eval_criteria | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | HoangL | Done | iter3 | none
33 | Trainee List | Supporter | class_user | List out the Trainees for a specific class in the system - The list also include the evaluated grades of the trainees (calculated automatically) - When changing trainee status to Dropped Out, the user need to input the dropout date - The Trainer also have the same access rights as the Supporter to the trainees list of the classes that he/she are assigned - From this page, the user can link to the Trainee Import & Trainee Details page s | KyNVC | Done | iter3 | none
34 | Trainee Import | Supporter | user, class_user | This is a pop-up screen where the user can import the new trainee list into a specific class - The import file should include limitted trainee information (full name, email) - New class trainees would be added into the selected class. In case any user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) | KyNVC | Done | iter3 | none
35 | Trainee Details | Supporter |  | Allow the user to input class trainee information for updating - The Trainer can also update class trainee information - Trainee basic information are read-only: full name, user name, email - Class trainee evaluation are read-only: on-going evaluation, final evaluation, topic evaluation - Class trainee information are editable: status, drop-out date, note | HoangL | Done | iter3 | none
36 | Schedule List | Supporter | schedule, class, class_setting | List out class schedules - Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Action - Actions: + View/Edit: link to the Schedule Details page to view/edit the relevant class schedule + Take Attendance: link to Attendance Details page to add/edit the class attendance of the relevant slot - this link is available only durent the training day of that slot - Global actions: + View Attendance: link to Attendance Tracking page + Add New: link to the Schedule Details page to add new class schedule - The Trainer have similar permissions as the Supporter on this page | DaiNH | Done | iter3 | none
37 | Schedule Details | Supporter | schedule, class, class_setting | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | DaiNH | Done | iter3 | none
38 | Attendance Tracking | Trainer | attendance, schedule | Allow the Supporter/Trainer to view the class trainees' attendance status of all the class schedules | AnhPT | Done | iter3 | none
39 | Attendance Details | Trainer | attendance, schedule | Allow the Supporter/Trainer to add/edit the class attendance of the relevant schedule | AnhPT | Done | iter3 | none
40 | Schedule Attendace | Trainee | attendance, schedule | List out class schedules of the selected class & the student attendance status for each schedule Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Attendance Status | AnhPT | Done | iter3 | none
41 | Team List | Trainer | team, team_member | See the Mockup - The Supporter & Trainee can view the team list & team details - Member Actions: Change Group, Remove Member, Set As The Leader - The screen just shows the active team-working assignments in the Assignment filter - Global Actions: + Create Groups or Reset Groups - link to New Teams page to create/re-create new team set + Remove Groups - remove or un-attached current team set from the selected milestone + Add New Group - add new group to change (move) a specific member to - Team Actions: + Add New Trainee: add trainee(s) from weighting list into the selected team + Team Details: link to Team Details to view and/or edit the team + Activate/Deactivate: activate or deactiavate the team - The above actions are not allowed for the team sets which are "attached" to the in-progress or closed milestones | DatLT | Done | iter3 | none
42 | New Teams | Trainer | team, team_member, submit | Allow the user to create groups or regroups See the Mockup - note to add one more tab called Clone Group with the similar layout as the Reuse Group; Clone Groups would create new team set "attached" to the milestone (by copying the current team configurations) instead of re-using the current team set in the Reuse Groups | KyNVC | Done | iter3 | none
43 | Team Details | Trainer | team, team_member, submit | Allow the user to input team information for updating relevant team or adding new team to the team set of the milestone. - Fields: team code, topic name, status, description - When creating new team, the default status value is Active | DatLT | Done | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Common | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | HoangL | Done | Iter1 | Iter1
2 | Demo Dashobard | Common | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | HoangL | To Do | Iter1 | Iter1
3 | User Login | Common | Fields: Email, Password, Capcha; Links: Reset Password, Register User can choose Google Login using the FPT @fpt.edu.vn account | KyNVC | Done | Iter1 | Iter1
4 | Password Reset | Common | Expiable new password link would be sent to the email for resetting Email -> Reset Link (Expirable) -> New Password, Verifying Password | KyNVC | Done | Iter1 | Iter1
5 | User Register | Common | Just input limited fields (full name, email, capcha), random access password sent via email; the user can by-pass registering with Google log-in | KyNVC | Done | Iter1 | Iter1
6 | User Profile | Common | o Allow the user to change the avatar, full name and view others (email, role) o The client can input/change his/her mobile, address, company, position o He/she can link to the Password Change screen below | HoangL | Done | Iter1 | Iter1
7 | Password Change | Common | Fields: Current Password, New Password, Verifying Password | AnhPT | Done | Iter1 | Iter1
8 | Setting List | Admin | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | AnhPT | Done | Iter1 | Iter1
9 | Setting Details | Admin | Fields: Type (L), Title, Value, Display Order, Status, Description | AnhPT | Done | Iter1 | Iter1
10 | User List | Admin | Filters: Role, Status Column: Id, Full Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Full Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | DatLT | Done | Iter1 | Iter1
11 | User Details | Admin | Fields: Id, Full Name, Email, Mobile, Role, Status, Note | DatLT | Done | Iter1 | Iter1
12 | Subject List | Manager | Filters: Manager, Expert, Status Column: Id, Code, Name, Manager, Expert, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ change the expert & status Status: Active, Inactive | DaiNH | Done | Iter1 | Iter1
13 | Subject Details | Manager | Fields: Code, Name, Manager (L), Expert (L), Status, Description | DaiNH | Done | Iter1 | Iter1
14 | Web Contact List | Supporter | Show the list of assigned web contacts | DatLT | Done | Iter1 | Iter1
15 | Web Contact Details | Supporter | View/Edit an assigned web contact | DaiNH | Done | Iter1 | Iter1

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | System Permissions | Admin | Configure the access permissions to each of the system roles to each of the system screens (the Admin role has all permissions to all the page and those permissions are not editable) | KyNVC | Done | Iter2 | Iter2
2 | User Authorization | System | Show/hide system menu (main, sider) following the role permissions Check the case when user enter URL directly in the Address box of the browser: - In case the user has not logged-in yet or the log-in session has expired, User Login page would be shown to authenticate user before coming back to the entered URL - If the logged in user has no right the the relevant page, the error page would be shown | KyNVC | Done | Iter2 | Iter2
3 | Subject Setting List | Manager | List out the Settings for a specific active subject in the system. From this page, the user can link to the Subject Setting Details page for adding new or updating a specific Setting. | DaiNH | Done | Iter2 | Iter2
4 | Subject Setting Details | Manager | Allow the user to input Subject Setting information for adding or updating. The user can not change the Subject and setting type when updating the Setting | DaiNH | Done | Iter2 | Iter2
5 | Assignment List | Manager | List out the Assigments for a specific active subject in the system. From this page, the user can link to the Assignment Details page for adding new or updating a specific Assignment. | DaiNH | Done | Iter2 | Iter2
6 | Assignment Details | Manager | Allow the user to input Assignment information for adding or updating (the user can not change the subject on updating the Assignment) | DatLT | Done | Iter2 | Iter2
7 | Eval Criteria List | Manager | configure the access permissions to each of the system roles to each of the system screens (the Admin role has all permissions to all the page and those permissions are not editable) | DatLT | Done | Iter2 | Iter2
8 | Eval Criteria Details | Manager | Allow the user to input Evaluation Criteria information for adding or updating (the user can not change the subject & assignment on updating the Evaluation Criteria) | DatLT | Done | Iter2 | Iter2
9 | Class List | Manager | List out the Classes in the system - The user can link to the Class Details, Attendance Tracking & Class Evaluations pages - The Trainer & Supporter users have also accesses to this page + The Trainer and Supporter users can see the Classes they are assigned + The links to the Attendance Tracking & Class Evaluations pages + The Supporter can change the Class status directly on this page or link to the Clas Details page for changing some class information (trainer, status, description) | AnhPT | Done | Iter2 | Iter2
10 | Class Details | Manager | Show the list of the Class data fields for viewing, updating or newly adding - The Manager user can update the Class information (except for the Subject) - The Supporter & Trainer user can view the Class information; The Supporter user can change some class information (trainer, status, description) | AnhPT | Done | Iter2 | Iter2
11 | Class Setting List | Trainer | List out the Settings for a specific active class in the system. - The Supporter can view the list of Settings for the classes that he/she are assigned (read-only) - From this page, the user can link to the Class Setting Details page for adding new or updating a specific Setting. | KyNVC | Done | Iter2 | Iter2
12 | Class Setting Details | Trainer | Allow the user to input Class Setting information for adding or updating - The user can not change the Class and setting type when updating the Setting - The Supporter can view the Class Setting information only | AnhPT | Done | Iter2 | Iter2
13 | Milestone List | Trainer | List out the Milestones for a specific active class in the system. - The Supporter can view the list of Milestones for the classes that he/she are assigned (read-only) - From this page, + The user can link to the Milestone Details page for viewing or updating a specific Milestone. + The Trainer can link to the New Milestone page for adding new Milestone - Status: Open -> In Progress -> Closed + The user can delete the Open milestone physically + When the user change the milestone status from Open to In-Progress, a pop-up would be shown informing the user about the teaming status & get confirmation about the teaming way to work on the milestone assignment (team-work, individually) + give him/her another option to come to the Team List page to configure milestone teaming + When the user change the milestone status from In-Progress to Closed, a pop-up would be shown informing him/her about the milestone evaluation status/results, explaining him that he/she can not update the evaluation for the closed milestone & get his/her confirmation on that + give him/her another option to come to the Milestone Evaluations page to view & update/adjust evaluations | HoangL | Done | Iter2 | Iter2
14 | New Milestone | Trainer | Allow user to input Milestone information for adding new: title, assignment, from date, to date There is not any case where one assignment is "linked" to more than one milestones or vise versa After submitting the page: - The information from selected assignment would be copied to the newly created Milestone: + The ass_body is copied to the milestone descriptions + The activate evaluation criteria are copied to the milestone's evaluation criteria | HoangL | Done | Iter2 | Iter2
15 | Milestone Details | Trainer | The Supporter and Trainer can view Milestone's information. The Trainer can edit Milestone's information (except for changing the linked assignment). | HoangL | Done | Iter2 | Iter2

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Class Eval-Criteria List | Trainer | List out the Evaluation Criteria for a specific class milestone in the system. The Supporter can view the Evaluation Criteria for the classes that he/she are assigned From this page, the user can link to the Class Eval-Criteria Details page for adding new (by cloning an existing Class Evaluation Criteria or adding brand new one) or updating a specific Class Evaluation Criteria | HoangL | Done | Iter3 | Iter3
2 | Class Eval-Criteria Details | Trainer | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | HoangL | Done | Iter3 | Iter3
3 | Trainee List | Supporter | List out the Trainees for a specific class in the system - The list also include the evaluated grades of the trainees (calculated automatically) - When changing trainee status to Dropped Out, the user need to input the dropout date - The Trainer also have the same access rights as the Supporter to the trainees list of the classes that he/she are assigned - From this page, the user can link to the Trainee Import & Trainee Details page s | KyNVC | Done | Iter3 | Iter3
4 | Trainee Import | Supporter | This is a pop-up screen where the user can import the new trainee list into a specific class - The import file should include limitted trainee information (full name, email) - New class trainees would be added into the selected class. In case any user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) | KyNVC | Done | Iter3 | Iter3
5 | Trainee Details | Supporter | Allow the user to input class trainee information for updating - The Trainer can also update class trainee information - Trainee basic information are read-only: full name, user name, email - Class trainee evaluation are read-only: on-going evaluation, final evaluation, topic evaluation - Class trainee information are editable: status, drop-out date, note | HoangL | Done | Iter3 | Iter3
6 | Schedule List | Supporter | List out class schedules - Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Action - Actions: + View/Edit: link to the Schedule Details page to view/edit the relevant class schedule + Take Attendance: link to Attendance Details page to add/edit the class attendance of the relevant slot - this link is available only durent the training day of that slot - Global actions: + View Attendance: link to Attendance Tracking page + Add New: link to the Schedule Details page to add new class schedule - The Trainer have similar permissions as the Supporter on this page | DaiNH | Done | Iter3 | Iter3
7 | Schedule Details | Supporter | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | DaiNH | Done | Iter3 | Iter3
8 | Attendance Tracking | Trainer | Allow the Supporter/Trainer to view the class trainees' attendance status of all the class schedules | AnhPT | Done | Iter3 | Iter3
9 | Attendance Details | Trainer | Allow the Supporter/Trainer to add/edit the class attendance of the relevant schedule | AnhPT | Done | Iter3 | Iter3
10 | Schedule Attendace | Trainee | List out class schedules of the selected class & the student attendance status for each schedule Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Attendance Status | AnhPT | Done | Iter3 | Iter3
11 | Team List | Trainer | See the Mockup - The Supporter & Trainee can view the team list & team details - Member Actions: Change Group, Remove Member, Set As The Leader - The screen just shows the active team-working assignments in the Assignment filter - Global Actions: + Create Groups or Reset Groups - link to New Teams page to create/re-create new team set + Remove Groups - remove or un-attached current team set from the selected milestone + Add New Group - add new group to change (move) a specific member to - Team Actions: + Add New Trainee: add trainee(s) from weighting list into the selected team + Team Details: link to Team Details to view and/or edit the team + Activate/Deactivate: activate or deactiavate the team - The above actions are not allowed for the team sets which are "attached" to the in-progress or closed milestones | DatLT | Done | Iter3 | Iter3
12 | New Teams | Trainer | Allow the user to create groups or regroups See the Mockup - note to add one more tab called Clone Group with the similar layout as the Reuse Group; Clone Groups would create new team set "attached" to the milestone (by copying the current team configurations) instead of re-using the current team set in the Reuse Groups | KyNVC | Done | Iter3 | Iter3
13 | Team Details | Trainer | Allow the user to input team information for updating relevant team or adding new team to the team set of the milestone. - Fields: team code, topic name, status, description - When creating new team, the default status value is Active | DatLT | Done | Iter3 | Iter3

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4