## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
User Login Screen | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | 1 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/21 | Open | KyNVC | 2022-04-17 04:55 | 2022-04-23 16:45 | iter2 | WP, 2_Doing | User Login
Write SRS for User Login screen | Write detailed functional specification for the User Login screen | 2 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/22 | Closed | KyNVC | 2022-04-17 04:57 | 2022-04-18 16:45 | iter2 | Task, 3_Done | User Login
Write SDS for User Login screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen | 3 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/23 | Closed | KyNVC | 2022-04-17 04:59 | 2022-04-18 16:44 | iter2 | Task, 3_Done | User Login
Write Code for User Login screen | Code & Unit test for the User Login screen | 4 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/24 | Open | KyNVC | 2022-04-17 05:00 | 2022-04-23 16:45 | iter2 | Task, 2_Doing | User Login
Integrate User Login screen with others | Integrate the User Login screen with other screens | 5 | https://gitlab.com/fu-kiennt-fall22/se1627-net_swp391/g6/-/issues/25 | Closed | KyNVC | 2022-04-17 05:01 | 2022-04-18 16:45 | iter2 | Task, 1_To Do | User Login